## operations and midyear
MONTH | OPERATIONS | ENFORCEMENT
JUNE | MAWS | CMPJ | CMPJ
JULY | CMPJ | MAWS | MAWS
AUGUST | MAWS | CMPJ | DNEC
SEPTEMBER | CMPJ | MAWS | SDUN
OCTOBER | MAWS | CMPJ
NOVEMBER | CMPJ | MAWS
DECEMBER | MAWS | CMPJ
WHAT | NTC MIDYEAR GENERAL ASSEMBLY
WHEN | JUNE 27-29,2022 | ITO FINAL NA
WHERE | ZOOM | <---FINAL NA DAW?
| PAGADIAN-WITH GROUND BREAKING | priority for groundbreaking
LAKEWOOD,ALINDAHAW
ERIBERTA SPRING
DIPOLOG
ROYAL FARM
ZAMBOANGA
CALI FARMS
NTC CONFERENCE ROOM
SANTIAGO?
SKYVIEW 20K LANG ROOM LANG WALA PA FOODS

## projects
| noa | BIDDER RECEIVED | contract/SUPPLIER | contract/OFFICE | ntp/ISSUED | ntp/EFFECTIVITY | NTP/RECEIVED | 120 DAYS |  | ACTION TO BE TAKEN
Various PPES | [8 empty] | CURRENT DELAY
Lenin ICT Equipment - Lot 3 | 10-27-2021 | 2021-08-11 | 11-18-2021 | 11-18-2021 | 12-20-2021 |  |  | February 27, 2022
HY Furnitures - Lot 1 | 10-27-2021 | 2021-05-11 | 11-26-2021 | 11-26-2021 | 10-30-2021 | 12-20-2021 | 11-26-2021 | March 20, 2022
[5 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 03-31-2022 |  | NEEDS TO SIGN NTP AGAIN AND MAKE LETTER TO ASK FOR EXTENSION
MBRB - Lot 2 & 4
LOT 2 | 11-22-2021 | 2021-09-12 | 12-17-2021 | 2022-07-01 | 11-25-2021 |  | 2021-09-12
[5 empty] | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-05 |  | NEEDS TO SIGN NTP AGAIN AND MAKE LETTER TO ASK FOR EXTENSION
LOT 4 | 11-22-2021 | 2021-09-12 | 12-17-2021 | 2022-07-01 | 11-25-2021 |  | 2021-09-12
[5 empty] | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-05 |  | NEEDS TO SIGN NTP AGAIN AND MAKE LETTER TO ASK FOR EXTENSION
NTC Edge - Lenin | DELIVERED
| 2021-10-11 | 11-17-21 | 11-19-2021 | 11-19-2021 | 11-20-2021 |  | 12-14-2021
|  |  | 39 DAYS |  |  |  |  | 60 DAYS | REQUEST FOR EXTENSION
Vehicle - Nissan LOT 2 | 3-14-2022 | 3-17-2022 | 3-17-2022 | 4-25-2022 | 3-25-2022 |  |  | May 24, 2022 | 2022-05-06 | WRITTEN REQUEST FOR THEIR MOTION FOR EXTENSION
| 3-14-2022 | 3-15-2022 | 3-17-2022 | 4-25-2022 | 4-26-2022 |  |  | 6-25-2022
Antenna - MBRB LOT 1 | 3-14-2022 | 3-17-2022 | 3-18-2022 | 4-25-2022 | 3-25-2022 |  |  | May 24, 2022 |  | TALK TOMORROW
[5 empty] | 4-26-2022 |  |  | 6-25-2022
Note on E13: late notarization